## RTM-Maisam
Test Senario | Req. ID | Requirement Description | Summary | Preconditions | Test Data | Steps to Reproduce | Expected Result | Actual Result | Status | Bug. ID
Verify the main page features work | R4.1 | The app must be Install The app open easily | Validate the Lest's Go icon work | 1-Install the app in your device 2-Connected to internet |  | 1-Open the app 2-Click on the Let's Go icon | The Let's Go icon work | The icon work | Passed
| R4.1 | The system have the Ability to choose a language by user | Validate the Choose Language dropdown list work |  |  | 1-Open the app 2-Click on Choose language list 3-Choose the language you want 4-The app will be changed to the language you have chosen | The Choose Language list work | The turkey option in the list didn't work | Failed | Def-01
| R4.1 | The Overview visible to read | Validate the general overview of the application available |  |  | 1-Open the app 2-Read the overview in top of the page | The application overview is available | Available overview | Passed
| R4.2 | The system have the differant features that allow users to discover the application,moving between pages ,make search and other | Validate the Basima Abu Ali icon work |  |  | 1-Click on Let's Go icon 2-Click on Basima Abu Ali icon in the Home page 3-Move to the next page | The Basima Abu Ali icon work | The icon work | Passed
| R4.2 |  | Validate the Facebook icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Basima Abu Ali icon 4-Click on Facebook icon 5-Move to Facebook website | Ability moving to Facebook website | The icon not work , can't move to Facebook | Failed | Def-02
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Basima Abu Ali icon 4-Click on map icon 5-Move to map website | Ability moving to map website | The icon work | Passed
| R4.2 |  | Validate the ability to navigate between images |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Basima Abu Ali icon 4-Navigate between images on the top of the page | Ability to navigate between images | This feature is available | Passed
| R4.2 |  | Validate scrollable the page |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Basima Abu Ali icon 4-Scrollable the page | Ability to scrollable the page | The Scrollable feature work | Passed
| R4.2 |  | Validate Abraham's Herberge/Beit Ibrahim icon is clickable |  |  | 1-Click on Let's Go icon 2-Click on Abraham's Herberge/Beit Ibrahim icon in the Home page 3-Move to the next page | Abraham's Herberge/Beit Ibrahim icon is clickable | The icon work | Passed
| R4.2 |  | Validate the phone icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Click on phone icon 5-Choose the option you want to make a call | The phone icon work | The icon work | Passed
| R4.2 |  | Validate the Facebook icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Click on Facebook icon 5-Move to Facebook website | The Facebook websit opens | This Facebook website not work | Failed | Def-03
| R4.2 |  | Validate the world icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Click on world icon 5-Move to world website | The world icon display and clickable | The world icon can't clickable and display | Failed | Def-04
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Click on map icon 5-Move to map website | The map icon display and clickable | The icon work | Passed
| R4.2 |  | Validate scrollable the page |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Scrollable the page | Ability to scrollable the page | The Scrollable feature work | Passed
| R4.2 |  | Validate the ability to navigate between images |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Abraham's Herberge/Beit Ibrahim icon 4-Navigate between images on the top of the page | Ability to navigate between images | This feature is available | Passed
| R4.2 |  | Validate Dar Al-Majus Community Home icon is clickable |  |  | 1-Click on Let's Go icon 2-Click on Dar Al-Majus Community Home icon in the Home page 3-Move to the next page | Dar Al-Majus Community Home icon is clickable | The icon work | Passed
| R4.2 |  | Validate the phone icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Dar Al-Majus Community Home icon 4-Click on phone icon 5-Choose the option you want to make a call | The phone icon work | The icon work | Passed
| R4.2 |  | Validate the Facebook icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Dar Al-Majus Community Home icon 4-Click on Facebook icon 5-Move to Facebook website | The Facebook websit opens | This Facebook website not work | Failed | Def-05
| R4.2 |  | Validate the world icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Dar Al-Majus Community Home icon 4-Click on world icon 5-Move to world website | The world icon display and clickable | The world icon can't clickable and display | Failed | Def-06
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Dar Al-Majus Community Home icon 4-Click on map icon 5-Move to map website | The map icon display and clickable | The icon work | Passed
| R4.2 |  | Validate Jacir place Hotel icon clickable |  |  | 1-Click on Let's Go icon 2-Click on Jacir place Hotel icon in the Home page 3-Move to the next page | Jacir place Hotel icon is clickable | The icon work | Passed
| R4.2 |  | Validate the phone icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Click on phone icon 5-Choose the option you want to make a call | The phone icon work | The icon work | Passed
| R4.2 |  | Validate the Facebook icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Click on Facebook icon 5-Move to Facebook website | The Facebook websit opens | This Facebook website not work | Failed | Def-07
| R4.2 |  | Validate the world icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Click on world icon 5-Move to world website | The world icon display and clickable | The world icon can't clickable and display | Failed | Def-08
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Click on map icon 5-Move to map website | The map icon display and clickable | The icon work | Passed
| R4.2 |  | Validate the ability to navigate between images |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Navigate between images on the top of the page | Ability to navigate between images | This feature is available | Passed
| R4.2 |  | Validate scrollable the page |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Jacir place Hotel icon 4-Scrollable the page | Ability to scrollable the page | The Scrollable feature work | Passed
| R4.2 |  | Validate The Walled off Hotel icon display and clickable |  |  | 1-Click on Let's Go icon 2-Click on The Walled off Hotel icon in the Home page 3-Move to the next page |  | The icon work | Passed
| R4.2 |  | Validate Hosh Al Syrian icon displayed and clickable |  |  | 1-Click on Let's Go icon 2-Click on Hosh Al Syrian icon in the Home page 3-Move to the next page | Hosh Al Syrian icon is clickable | The icon work | Passed
| R4.2 |  | Validate Hosh Mar Jeriyes icon display and clickable |  |  | 1-Click on Let's Go icon 2-Click on Hosh Mar Jeriyes icon in the Home page 3-Move to the next page | Hosh Mar Jeriyes icon is clickable | The icon work | Passed
| R4.2 |  | Validate Casanova icon displayed and clickable |  |  | 1-Click on Let's Go icon 2-Click on Casanova icon in the Home page 3-Move to the next page | Casanova icon is clickable | The icon work | Passed
| R4.2 |  | Validate the Ibrahimi Mosque icon displayed and clickable |  |  | 1-Click on Let's Go icon 2-Click on Ibrahimi Mosque icon in the Home page 3-Move to the next page | Ibrahimi Mosque icon is clickable | The icon work | Passed
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Ibrahimi Mosque icon 4-Click on map icon 5-Move to map website | The map icon display and clickable | The icon work | Passed
| R4.2 |  | Validate the Al-Haras mosque icon displayed and clickable |  |  | 1-Click on Let's Go icon 2-Click on Al-Haras mosque icon in the Home page 3-Move to the next page | Al-Haras mosque icon work | The icon work | Passed
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Al-Haras mosque icon 4-Click on map icon 5-Move to map website | Al-Haras mosque icon work | The icon work | Passed
| R4.2 |  | Validate Othman bin Affan Mosque icon displayed and clickable |  |  | 1-Click on Let's Go icon 2-Click on Othman bin Affan Mosque icon in the Home page 3-Move to the next page | Othman bin Affan Mosque icon work | The icon work | Passed
| R4.2 |  | Validate the map icon work |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Othman bin Affan Mosque icon 4-Click on map icon 5-Move to map website | The map icon display and clickable | The icon work | Passed
Verify the Search icon features | R4.3 |  | Validate Search icon clickable and functions as it should |  |  | 1-Click on the Let's Go icon 2-Move to the Home page 3-Click on Search icon in the buttom of the page 4-Move to next page | The Search icon display and clickable | The icon work | Passed
| R4.3 |  | Validate make Search by choose the Name |  | Name:Basima Abu Ali | 1-Click on the Search icon in the home page 2-Choose the name of place you want 3-Click on Search button | Search by Name work | As Expected | Passed
| R4.3 |  | Validate make Search by choose the City |  | City:Hebron | 1-Click on the Search icon in the home page 2-Choose the City you want to make Search about it 3-Click on Search button | Search by City work | As Expected | Passed
| R4.3 |  | Validate make Search by choose the Categorys |  | Category:Local Food - Public Spaces | 1-Click on the Search icon in the home page 2-Choose the Categorys you want to make Search about it 3-Click on Search button |  | As Expected | Passed
| R4.3 |  | Validate make Search by more than one choose |  | City:Bethlehem Category:Hotel | 1-Click on the Search icon in the home page 2-Choose the name of place you want 3-Choose the City you want to make Search about it 4-Choose the Categorys you want to make Search about it 3-Click on Search button |  | As Expected | Passed
| R4.3 |  | Validate Unclick on the City you choose |  |  | 1-Click on the Search icon in the home page 2-Choose the City you want to make Search about it 3- Make Unclick on the City you chose | Ability to make unclick on the city filed that chosen | Disability to make Unclick on the chosen field | Failed | Def-09
| R4.3 |  | Validate make Search by Name to site that is not in the system |  | Name:Hisham palace | 1-Click on the Search icon in the home page 2-Choose the Name of site you want to make Search about it 3- Make click on theSearch button | No Result | As Expected | Passed

## RTM-Lina
Req. ID | Requirement Name | Requirement Description | Requirement Section | Test Case ID | Summary | Preconditions | Test Data | Steps to Reproduce | Expected Result | Actual Result | Status | Bug. ID
R4.1 | Main Page | The main page includes an introduction paragraph and a main button to continue, along with language choices. | R4.1 | MainPage -01 | Check opening the app successfully | The app is installed |  | 1- Open the app | The app is opened successfully | As Expected | Passed
R4.1 | Main Page |  | R4.1 | MainPage -02 | Verify Introduction Pragraph is displayed in the main page | The app is installed |  | 1. Open the app 2. Check that the introduction pragraph is displayed 3. Navigate to "Let's Go" button. 4. Press on button 5. Check redirecting to the next page | Text introduciton paragraph is displayed and the "Let's Go" button is available , clickable and functions well . | As Expected | Passed
R4.1 | Main Page |  | R4.1 | MainPage -03 | Verify that the language list is available, clickable and that the page is updated when selected | The app is installed |  | 1. Open the app 2. Navigate to Choose language list 3. Choose Arabic, English, Turkish, Espaniol,Italy, Romanio 4. Check that introduction language displayed in selected language | "Choose languae" list is available, clickable, and the page is updated based on selected language | The app is crashed and fail when choose turkish language | Failed | Bug #01
R4.1 | Main Page |  | R4.1 | MainPage -04 | Check the Main icon is clickable and functions well and contains the main tabs | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on main icon button at the top right of the page | Main Button is clickable and functions well | As Expected | Passed
R4.2 | Home page | The page contains several categories with lists that users can navigate through. It also displays photos, links for WhatsApp, the website, phone, location, and additional buttons. | R4.2.3 Cultural Organization | HomePage -01 | Check that Home page is displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Check that Home tab is displayed 4. Click on "Home" tab | Home button is clickable | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -02 | Check scrolling up and down in the page | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Check that Home tab is displayed 4. Scroll up and down | Scrolling functions well | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -03 | Check that Cultural Organization is displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Scroll down 4. Click on "Cultural Organization" tab | Cultural organization is clickable | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -04 | Check that the lists in the Cultural Organization are displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Cultural Organization" tab 4. Click on "Freedom Theatre" | Freedom Theatre page is displayed | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -05 | Check that the phone icon is clickable and functions well in (Cultural Organization) page | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Cultural Organization" tab 4. Click on "Freedom Theatre" 5. Click on Phone icon 6. Click on Back icon | Phone icon is available and functions well | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -06 | Check that the location buttion is clickable and functions well in (Cultural Organization) page | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Cultural Organization" tab 4. Click on "Freedom Theatre" 5. Click on Location icon | Location icon is available and functions well | As Expected | Passed
R4.2 | Home page |  | R4.2.3 Cultural Organization | HomePage -07 | Check that the back buttion is clickable and functions well in (Cultural Organization) page | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Cultural Organization" tab 4. Click on "Freedom Theatre" 5. Click on Location icon 6. Click on Back home button 7. Click on Back icon in app | Back icon is displayed and functions well | As Expected | Passed
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -08 | Check that Gifts and Oriental Antiques is displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab | Gifts and Oriental Antiques list is avialiable and clickable | As Expected | Passed
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -09 | Check that the phone button in (Gifts and Oriental Antiques) is clickable and functions | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4. Click on "Arafa Perfume Shop" 5. Click on Phone button | Phone button is clickable and fucntions well | As Expected | Passed
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -10 | Check that the location buttion in (Gifts and Oriental Antiques) is clickable and functions well | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4.Click on "Location" button | Location Button is clickable and functions well | As Expected | Passed
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -11 | Check that more icon in (Gifts and Oriental Antiques) is displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4.Click on "Location" button | More button is clickable and redirect to the next page | As Expected | Passed
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -12 | Check that the whatsapp icon functions well | The app is installed and the Gifts page contains whatsapp icon |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4. Click on "Al Salam for Glass" 5. Click on Whastapp icon | Whatsapp icon functions well and redirect to whatsapp | Page is not found | Failed | Bug #02
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -13 | Check that the website icon is clickable and functions well | The app is installed and the Gifts page contains Webpage icon |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4. Click on "Al Salam for Glass" 5. Click on www icon | www icon functions well and redirect to the webpage | Website Icon in not clickable | Failed | Bug #03
R4.2 | Home page |  | R4.2.4 Gifts and Oriental Antiques | HomePage -14 | Check that the photos are clickable and opened successfully | The app is installed |  | 1. Open the app 2. Click on "Let's Go" button. 3. Click on "Gifts and Oriental Antiques" tab 4. Click on "Al Salam for Glass" 5. Click on the photos | Photos are opened successfully | As Expected | Passed
R4.4 | Add Facility | This page enables users to add their facilities, including essential fields such as name, city, category, address, and description, along with upload photos. | R4.4 | AddFacility - 01 | Check that Add Your Facility tab is displayed and clickable | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button | Add your facility button is available and clickable | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 02 | Check that facility tab contains required info | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button 4. Check that the "Add facility" button includes all required fields | Add your facilitiy page contains all required fields | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 03 | Check that all filed are editable | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Name" button 4. Fill the Fields | All fields in "Add your facility" page are clickable and editable | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 04 | Check selecting from the City and Category Lists | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Select City" List 4. Click on "Bethlehem" 5. Click on "Select Category" List 6. Click on "Hotel" | Bethlehm City is selected and also Hotel Category is selected | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 05 | Check uploading and select photos to the "Add Your Facility" form | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Select City" List 4. Click on "Bethlehem" 5. Click on "Select Category" List 6. Click on "Hotel" 7. Fill all the required fields with valid data 8. Click on image icon 9. Select photo 10 .Click on Submit | Photo is uploaded and added | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 06 | Check that submit button is displayed and functions well | The app is installed |  | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button 4. Fill the fields 5. Click on "Submit" button | Submit button is displayed and clickable | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 07 | Check adding invalid data and submit the form | The app is installed | { Name: My Name City: Bethlehm Category: Hotel Phone: 0598 Whatsapp: 0598 Facebook: 05098 Address: Street 01 - Near Market Description: Description trial image : upload image } | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button 4. Fill the fields with invalid data 5. Click on "Submit" buttion | Submit facility wih invalid data is rejected | The form is submitted with success message | Failed | Bug #04
R4.4 | Add Facility |  | R4.4 | AddFacility - 08 | Check that success message is displayed after submit form with valid data and that it is accepted | The app is installed | { Name: Name City: Bethlehm Category: Hotel Phone: 0598111111 Address: Nablus Description: Description trial image : upload image } | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button 4. Fill the fields with valid data 5. Click on "Submit" buttion 6. Check that the message is displayed 7. Click on "Okay" | Success message is displayed and accepted | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 09 | Check adding facility without insert the city | The app is installed | { Name: Name City: Leave the field empty } | 1. Open the app 2. Click on "main" button. 3. Click on "Add Your Facility" button 4. Fill the fields with valid data 5. Click on "Submit" buttion 6. Click on Add facility button | Error message is displayed and it is rejected | As Expected | Passed
R4.4 | Add Facility |  | R4.4 | AddFacility - 10 | Check adding multiple faciities with the same name | The app is installed | { Name: Name City: Bethlehm Category: Hotel Phone: 0598111111 Address: Nablus Description: Description trial image : upload image } | 1. Open the app 2. Click on "main" button. 3. Click on "Add facility" button 4. Fill the fields with valid data 5. Click on "Submit" buttion 6. Fill the fields with the same name again 7. Click on Submit | Submit form is rejected | As Expected | Passed

## RTM-Judah
Test Case ID | Description | Requirements | Test steps | Pre-conditions | Test data | Expected output | Test status | Bug ID
R 6.1 | Verfiy the ability to enter the application | The system must allow the user to enter | Click on the app Icon | Application installed | N/A | The app oppens | Passed |  |  | 1
R 6.2 | Verfiy the ability to change language | The system user must allow the user | Open the app | Application installed | N/A | language changes | Passed |  |  | 2
|  | to choose a language | Wait for the screen to load
Choose from the list
R 6.3 | Verfiy the ability to navigate to cities frame | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 3
|  | to open cities frame | Wait for the screen to load
Click on Cities in the bar down
R 6.4 | Verfiy the ability to return to the main screen | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 4
|  | to return to the main screen | Wait for the screen to load
Click on Cities in the bar down
Click on the three dots in the top
right
Click on home from the list
R 6.5-1 | Verfiy the ability to selecet Bethlehem from cities | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 5
|  | to selecet Bethlehem form cities | Wait for the screen to load
Click on Cities in the bar down
Click on the targeted city from the
list
R 6.5-2 | Verfiy the ability to selecet Jenin from cities | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 6
|  | to selecet Jenin form cities | Wait for the screen to load
Click on Cities in the bar down
Click on the targeted city from the
list
R 6.5-2 | Verfiy the ability to selecet Hebron from cities | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 7
|  | to selecet Hebron form cities | Wait for the screen to load
Click on Cities in the bar down
Click on the targeted city from the
list
R 6.6 | Verfiy the ability to return to the main screen | The system user must allow the user | Open the app | Application installed | N/A | New frame is loaded | Passed |  |  | 8
|  | to return to the main screen from targeted cities | Wait for the screen to load
|  | frame | Click on Cities in the bar down
Click on the targeted city from the
list
press the < in the top of the page
R 6.7 | Verfiy the ability to watch the Promo video | The system must allow the user to watch the prom | Navigate through the Bethelehem | Application installed | N/A | New frame is loaded and the video | Failed |  |  | 9
|  | video | frame. |  |  | is started
Click on promo video
R 6.8-1 | Verfiy the ability to exit the video from the X bar | The system must allow the user to exit the video | Click on the X | Application installed | N/A | Bethlehem main screen is loaded | Passed |  |  | 10
R 6.8-1 | Verfiy the ability to exit the video from the <== | The system must allow the user to exit the video | Click on the <== | Application installed | N/A | Bethlehem main screen is loaded | Passed |  |  | 11
indicator
R 6.9 | Verfiy the ability to read more about Bethlehem | The system must allow the user to see more text | Click on read more from Bethlehem | Application installed | N/A | More info is presented to the user | Passed |  |  | 12
frame
R 6.10 | Verfiy the ability to watch the Virtual tour | The system must allow the user to watch the Virtual | Navigate through the Bethelehem | Application installed | N/A | New frame is loaded and the tour | Passed |  |  | 13
|  | tour | frame. |  |  | is started
Click on Virtual tour
R 6.11 | Verfiy the ability to exit the tour from the X bar | The system must allow the user to exit the video | Click on the X | Application installed | N/A | Bethlehem main screen is loaded | Passed |  |  | 14
R 6.12 | Verfiy the ability to change the view from the drop | The system must allow the user to change the view | Click on the drop down list | Application installed | N/A | Virtual tour frame changes | Passed |  |  | 15
down list
R 6.13 | Verfiye the ability to see the Album images | The system must allow the user to watch the Album | Navigate through the Bethelehem | Application installed | N/A | New frame is loaded and the images | Passed |  |  | 16
|  |  | frame. |  |  | are presented
Click on Album
R 6.14 | Verfiy the ability to see the pictures from the cities | The system must allow the user to watch the pictures | Click on the images | Application installed | N/A | Image displayed | Passed |  |  | 17
R 6.15 | Verfiy the ability to exit the album from the X bar | The system must allow the user to exit the video | Click on the X | Application installed | N/A | Bethlehem main screen is loaded | Passed |  |  | 18
R 6.16 | Verfiy the ability to play fun game | The system must allow the user to play the game | Navigate through the Bethelehem | Application installed | N/A | New frame is loaded | Passed |  |  | 19
frame.
Click on fun game
R 6.16 | Verfiye the ability to choose a game to play | The system must allow the user to choose a game to | Choose one of the games and | Application installed | N/A | New frame is loaded | Passed |  |  | 20
|  | play | click
R 6.17 | Verfiy the ability to return to the main frame using | The system must allow the user to return to the main | Click on the <== | Application installed | N/A | Play game main screen is loaded | Passed |  |  | 21
| <== indicator | frame
R 6.18 | Verfiye the ability to select Accommodation from the | The system must allow the user to select | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 22
| list | Accommodation from the list
R 6.19 | Verify the ability to contact with the target by the | The system must open phone dalire to make calls | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 23
phone number
R 6.19 | Verify the ability to open facebook page | The system must open facebook page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The page is not opening | 24
R 6.20 | Verify the ability to web page | The system must open web page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The element in not clickable | 25
R 6.21 | Verify the ability to open mapes | The system must provide maps for the place | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 26
R 6.22 | Verfiy the ability to return to the previous frame | The system must allow the user to return one step back | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 27
R 6.23 | Verfiy the ability to select Attractions from the | The system must allow the user to select | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 28
| list | Attractions from the list
R 6.24 | Verify the ability to contact with the target by the | The system must open phone dalire to make calls | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 29
phone number
R 6.25 | Verify the ability to open facebook page | The system must open facebook page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The page is not opening | 30
R 6.25 | Verify the ability to open whatsup page | The system must open whatsup page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The element in not clickable | 31
R 6.26 | Verify the ability to web page | The system must open web page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 |  | 32
R 6.27 | Verify the ability to open mapes | The system must provide maps for the place | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 33
R 6.28 | Verfiy the ability to return to the previous frame | The system must allow the user to return one step back | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 34
R 6.29 | Verfiy the ability to select Dining and resturants | The system must allow the user to select | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 35
| from the list | Dining and resturants from the list
R 6.30 | Verify the ability to contact with the target by the | The system must open phone dalire to make calls | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 36
phone number
R 6.31 | Verify the ability to open facebook page | The system must open facebook page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The page is not opening | 37
R 6.32 | Verify the ability to open whatsup page | The system must open whatsup page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 | The element in not clickable | 38
R 6.33 | Verify the ability to web page | The system must open web page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 |  | 39
R 6.34 | Verify the ability to open mapes | The system must provide maps for the place | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 40
R 6.35 | Verfiy the ability to return to the previous frame | The system must allow the user to return one step back | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 41
R 6.36 | Verfiy the ability to select Cultural organization | The system must allow the user to select | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 42
| from the list | Cultural organization from the list
R 6.37 | Verify the ability to contact with the target by the | The system must open phone dalire to make calls | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 43
phone number
R 6.38 | Verify the ability to open facebook page | The system must open facebook page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 |  | 44
R 6.40 | Verify the ability to web page | The system must open web page | Click on one of the elements | Application installed | N/A | New frame is open | Failed | B01 |  | 45
R 6.41 | Verify the ability to open mapes | The system must provide maps for the place | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 46
R 6.42 | Verfiy the ability to return to the previous frame | The system must allow the user to return one step back | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 47
R 6.36 | Verfiy the ability to select Gifts and Oriental Antiques | The system must allow the user to select | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 48
| from the list | Gifts and Oriental Antiques from the list
R 6.37 | Verify the ability to contact with the target by the | The system must open phone dalire to make calls | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 49
phone number
R 6.38 | Verify the ability to open facebook page | The system must open facebook page | Click on one of the elements | Application installed | N/A | New frame is open | Failed |  |  | 50
R 6.40 | Verify the ability to web page | The system must open web page | Click on one of the elements | Application installed | N/A | New frame is open | Failed |  |  | 51
R 6.41 | Verify the ability to open mapes | The system must provide maps for the place | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 52
R 6.42 | Verfiy the ability to return to the previous frame | The system must allow the user to return one step back | Click on one of the elements | Application installed | N/A | New frame is open | Passed |  |  | 53

## Test Summary Report
Test Summary Report
Project Name: | Tour Palestine App |  | Tester: |  | Lina Ramahi Maisam Salamah Judah Sleibi
Date of Report: | 2025-04-02
Test Summary Report #: | 1
Overall Status
Executed Tests | Passed |  | 100 |  | 79.37% of executed tests | 126
| Failed |  | 26 |  | 20.63% of executed tests
| No. (Total) Tests Executed (Passed + Failed) |  | 126
In Progress | [5 empty] | 0
Blocked | [5 empty] | 0
(Sub-total) Test Planned (not Executed) | [5 empty] | 0
Total Tests (Planned + Executed) | [5 empty] | 126
Test objective/feature | No. TCs Planned | No. TCs Executed | %TCs Executed | No. of Test Cases failed | No. of Test Cases passed | % TCs Passed to executed
Main and Home page | 56 | 56 | 100% | 11 | 45 | 80.36%
CIties page | 53 | 53 | 100% | 13 | 40 | 75.47%
Search page | 7 | 7 | 100% | 1 | 6 | 85.71%
Add your Facility | 10 | 10 | 100% | 1 | 9 | 90%
Total | 126 | 126 | 100% | 26 | 100 | 79.37%
Blockers or issues countered
1. Problems in the test environment
Excuted